## Cover sheet
Risk Operating Plan
The Balancing and Settlement Code (BSC), Section Z 5.5, requires the Performance Assurance Board (PAB) to prepare and maintain a Risk Operating Plan (ROP) setting out the risk mitigation activities, and Performance Assurance Techniques (PAT), for the Settlement Risks, as set out in the Risk Evaluation Register (RER), over the course of the Performance Assurance Operating Period (PAOP). The PAB reviews the ROP annually, and as appropriate within the year. A draft is provided to Performance Assurance Parties (PAP) and other interested parties for comment. Appropriate changes are made following consideration of these comments, after which the PAB approves and adopts the ROP.
| Version: | 0.1
| Effective From Date: | 2019-01-31
| Status: | Draft - For approval
| Contents: | Summary PAT Deployment
Targeted PAT Deployment
PAT Deployment Detail
Events Log
ROP Change Log
Where to find out more:
- visit https://www.elexon.co.uk/reference/performance-assurance/
- contact paa@elexon.co.uk

## Summary PAT Deployment
Technique | Standard Deployment | Notes on standard deployment | Targeted Deployment Expected - for detail see next tab
BSC Audit | The BSC Audit is now split into two distinct approaches: - ‘Central Systems’ and CVA Meter Operator Agents – remain within scope of the ISAE 3000 Assurance Opinion - Suppliers and Supplier Volume Allocation agents – are now in scope of a Process Assessment engagement under Performance Assurance Framework (PAF) | SVA Work Papers CVA Work Papers Central Systems Audit | R011 - Unmetered Supplies R016 - Energisation Status R003 - SVA Metering Equipment installation, programming, maintenance and Commissioning R021 - CVA Retrieval and processing of Metered Data R005 - SVA Fault Resolution R023 - CVA Fault Resolution R018 - Revenue Protection
Technical Assurance of Performance Assurance Parties | TAPAP review where Parties are meeting their Balancing and Settlement Code (BSC) obligations, to identify weakness in industry practices and detect any issues in the BSC processes. | Post-Qualification Check Compliance Check TA Check on audit issues | Late and Missing SMART MTDs R007 - SVA Retrieval of Metered Data R011 - Unmetered Supplies R005 - SVA Fault Resolution R023 - CVA Fault Resolution R018 - Revenue Protection
Technical Assurance of Metering | To check the compliance of Metering Systems, the Technical Assurance Agent (TAA) has to perform an annual audit made up of individual inspection visits. | Main Sample of SVA Sites Main Sample of CVA Sites - Potential for 3 Offshore Windfarms | R016 - Energisation Status R003 - SVA Metering Equipment installation, programming, maintenance and Commissioning R021 - CVA Retrieval and processing of Metered Data R005 - SVA Fault Resolution R023 - CVA Fault Resolution
Performance Assurance Reporting and Monitoring System | The PARMS database contains information about how Suppliers and their Supplier Hubs are performing. | Standard Serial Processing SP11 – Timely appointment of agents SP12 - Timely notification of changes to the Data Aggregator (DA) via D0148 SP13 - Timely notification of changes to the Meter Operator Agent (MOA) via D0148 SP15 – Missing Appointments of Agents HM11 - Timely Sending of Half-Hourly (HH) Meter Technical Details (MTDs) HM12 – Missing HH MTDs HM13 – Quality of HH MTDs HM14 - Timely HH Meter Investigation Requests NM11 - Timely Sending of Non-HalfHourly (NHH) Meter Technical Details (MTDs) NM12 – Missing NHH MTDs NC11 – Missing NHH Meter Reads & History from Old NHHDC to New NHHDC | R007 - SVA Retrieval of Metered Data R005 - SVA Fault Resolution R023 - CVA Fault Resolution
Supplier Charges | Supplier Charges are liquidated damages that Suppliers incur if they fail to meet certain performance levels. They compensate Parties disadvantaged by those who aren’t meeting defined Standards. | Standard calcuation, reporting and Supplier engagement SP01 - Delivery of Routine Performance Monitoring Reports SP02 - Delivery of Routine Performance Monitoring Logs SP04 - Installation of Half Hourly (HH) Metering SP08a - Percentage of Non-Half Hourly (NHH) Energy Settled on Annual Advances SP08b - Percentage of HH Energy Settled on Actual Readings SP08c - Percentage of non-mandatory HH Energy Settled on Actual Readings | R007 - SVA Retrieval of Metered Data
Peer Comparison | Public Peer Comparison and Quarterly Peer Comparison. The Performance Assurance Board (PAB) approves both of these types and the PARMS Serials that are to be published. |  | R007 - SVA Retrieval of Metered Data R005 - SVA Fault Resolution R023 - CVA Fault Resolution
Material Error Monitoring | Material Error Monitoring process to analyse settlement data and supplementary data to estimate and track identified material errors. | Erroneous Large Estimated Annual Consumption (EAC)/Annualised Advances (AAs) Unmetered Supplies (UMS) Incorrect Energisation Status | R007 - SVA Retrieval of Metered Data R011 - Unmetered Supplies R016 - Energisation Status R003 - SVA Metering Equipment installation, programming, maintenance and Commissioning R005 - SVA Fault Resolution R023 - CVA Fault Resolution
Error & Failures Resolution | An Error/Failure may be detected through the application of any Performance Assurance Technique. Upon detection the PAB can invoke the Error/Failure process. | BSC Audit Plans Top Risk Plans P322/P272 Plans P283 Plans AMR MTD Plans Missing MTD Plans Other Plans | R007 - SVA Retrieval of Metered Data R003 - SVA Metering Equipment installation, programming, maintenance and Commissioning R005 - SVA Fault Resolution R023 - CVA Fault Resolution R018 - Revenue Protection
Bulk Change of Agent | Bulk Change of Non Half Hourly Agent is designed to provide the BSC Panel and Performance Assurance Board (PAB) assurance that when responsibilities for large volumes of Non Half Hourly (NHH) Metering Systems change, it’s done in a controlled way.
Qualification | When entering the electricity market, a new organisation is required to complete SVA Qualification process to operate.
Re-Qualification | Existing Party Agents are required to maintain their Qualified status through the re-Qualification process. |  | R007 - SVA Retrieval of Metered Data R003 - SVA Metering Equipment installation, programming, maintenance and Commissioning R023 - CVA Fault Resolution
Removal of Qualification | The Performance Assurance Board (PAB) can remove a Qualified Person’s Qualification if the Qualified Person fails to comply with certain requirements and standards of the code. Error and Failure Resolution (EFR) and all escalation steps within BSCP538 must be completed before the RoQ process can be initiated. |  | R018 - Revenue Protection
Breach & Default | Formal notification may be provided to a BSC Party of persistent or material breach of the BSC. A failure to address this breach in all material respects with all reasonable diligence and so far as reasonably practicable may constitute a ‘Default’. |  | R007 - SVA Retrieval of Metered Data R003 - SVA Metering Equipment installation, programming, maintenance and Commissioning
Trading Disputes | Trading Dispute can arise where errors in the data, processes and/or rules used for the purposes of Settlement are identified and where such errors affect the amounts paid to or from Trading Parties. Trading Disputes can also arise as a result of errors in the determination of whether a Party is in Credit Default. |  | R018 - Revenue Protection
Education | ELEXON runs regular training sessions for people involved in the electricity industry. These include an overview of the BSC and specific sessions of key parts of working in the electricity industry. |  | R007 - SVA Retrieval of Metered Data R016 - Energisation Status R003 - SVA Metering Equipment installation, programming, maintenance and Commissioning R021 - CVA Retrieval and processing of Metered Data R005 - SVA Fault Resolution R023 - CVA Fault Resolution R018 - Revenue Protection
Change | The Balancing and Settlement Code (BSC) Change process is used to introduce changes to the BSC arrangements in response to any concerns, problems or defects that Parties may identify in the current processes. Under these processes, changes can be made to the BSC, its Code Subsidiary Documents (CSDs) and to BSC Systems. |  | R007 - SVA Retrieval of Metered Data R003 - SVA Metering Equipment installation, programming, maintenance and Commissioning

## Targeted PAT Deployment
Risk ref | Risk Title | Risk impact | Impact rationale | Target Risk impact | Target risk impact rationale | Risk factor / Control | PAP type | PAT/Approach
7 | SVA Metered data is not retrieved, such that the proportion of estimated data being used in Settlement contributes to performance standards not being met | £26.8m | Driven by the assessment of Annual Consumption by MC and PC. The Industry performance and the failure to retrieve metered data and the costs associated | £22m | Further assessment of Root Cause and a refreshed approach to mitigation should enable a continued increase in performance against this risk. | Site Access Issues | Supplier | EFR
[7 empty] | DC | MEM
Change
[6 empty] | Industry Knowledge | All | Education
[6 empty] | Poor Performance | Supplier | Re-qual / Breach and default
[6 empty] | Poor Performance | Supplier | Peer comparison
[6 empty] | Poor Performance | Supplier | Supplier Charges
[6 empty] | Poor Performance Insight | All | Analysis/RFI
[6 empty] | Poor Performance Insight | Supplier | TAPAP
[6 empty] | Performance Monitoring | Supplier | PARMS
In addition to establised Techniques deployed against this risk (EFR, MEM, Supplier Charges), we aim to provide further granularity and understanding around poor performance against this risk, by deploying investigatative techniques, such as TAPAP to challenge and clarify reasons for Metered Data not being retrieved. We would like to investigate, amongst other data items, age of EAC. This Risk will be investigated in conjuction with Risk 006 - Meter Technical Details transfer and processing
Risk ref | Risk Title | Risk impact | Impact rationale | Target Risk impact | Target risk impact rationale | Risk factor / Control | PAP type | PAT/Approach
11 | Unmetered Supplies volumes are calculated incorrectly or not at all | £17.6m | Impact is driven by assessment of volumes associated with UMS related Consumption Component Class (CCC) IDs from the DTN Data Flows. | £15.6m | Exploratory actions will allow us to re-assess risk impact more accurately | UMS Compliance | Supplier | BSC Audit
[7 empty] | LDSO | BSC Audit
[6 empty] | Lack of clarity for UMSO process | LDSO | TAPAP
[6 empty] | UMSO does not provide EAC to DC or DC not utilising provided EAC | LDSO | MEM
[6 empty] | Format of UMS Data | All | Analysis
Unmetered Supplies are an area which the Performance Assurance Framework has limited scope, largely due to limitations within both the process and the data available. Our aim in mitigating this risk is to establish stronger data sources, look at Cross Code links to better understand wider compliance issues. We aim to work with Suppliers and Unmeter Supply Operators to ensure that UMS inventories are accurate and up to date, to minimise settlement error.
Risk ref | Risk Title | Risk impact (£m) | Impact rationale | Target Risk impact (£m) | Target risk impact rationale | Risk factor / Control | PAP type | PAT/Approach
16 | The energisation status held in SMRS or by any party in the Supplier Hub does not match the physical energisation status of the SVA Metering System | £15.1m | Assessment of the mismatches Logical and Physical Energisation Status across PC and MC | £12m | Refreshed instance reporting alongside focus on Fault Resolution should see impact reduce in year. | incorrect notification of change | All | BSC Audit
Education
TAM
[6 empty] | Lack of Formal Reporting | All | MEM
Energisation Status mismatches cause a fundamental risk to Settlement. We have previously deployed techniques against this risk, however, we feel it is appropriate to re-assess this risk and provide a refreshed view of the performance against this risk, to enable parties to better manage and mitigate this risk
Risk ref | Risk Title | Risk impact (£m) | Impact rationale | Target Risk impact (£m) | Target risk impact rationale | Risk factor / Control | PAP type | PAT/Approach
3 | SVA Metering Equipment is installed, programmed or maintained incorrectly including where Commissioning is performed incorrectly or not at all | £43m | (why it got this rating in the RER) | £40m | whilst the change introduced in NOV will improve the impact, there will be a structured approach to the PATs in use across the year which should seek to reduce the impact further still | MC EFG Commissioning issues | All | Analysis
[6 empty] | Future changes to Commissioning compliance | All | Change
[6 empty] | Recently implemented changes | MOA | MEM
[7 empty] | LDSO | TAM
[7 empty] | MOA | EFR
[7 empty] | LDSO | Analysis
[7 empty] | All | Education
[6 empty] | Monitoring new Dataflows | MOA | BSC Audit
LDSO
[6 empty] | Performance Management | MOA | Re-qual / Breach and Default
LDSO
[6 empty] | Third Party Activities | LDSO | Change
Supplier
[6 empty] | Process Management | All
[6 empty] | Other Codes and Associations | All | Analysis
Meter Installation is a source risk and as such requires close attention to manage and mitigate. There has been significant changes and progress to this risk in recent months, with new dataflows released to aid in the management of Commissioning, in particular. In order to monitor the impact of these changes, we propose applying investigative techniques and analysis against these changes, in addition to continuing deployment of performance improvement techniques, such as EFR.
Risk ref | Risk Title | Risk impact | Impact rationale | Target Risk impact | Target risk impact rationale | Risk factor / Control | PAP type | PAT/Approach
21 | CVA metered data is not retrieved, or processed correctly, or at all, by the CDCA | £31.1m | (why it got this rating in the RER) | £24m | Specific focus in this area, looking at Service Level Agreements, should drive the impact down | Lack of Audit Controls | CVA MOA | BSC Audit
[7 empty] | CVA MOA | TAM
[6 empty] | Understand Central Service Processes | CVA MOA | Service delivery
Service delivery
Analysis
[7 empty] | CVA MOA | CVA consumption estimation
[6 empty] | Improve CVA awareness | CVA MOA | Education
Our focus for this risk is to understand the drivers and limitations for poor performance within CDCA. This will involve analysis of existing SLAs, Material Error and the GSP Estimation process. In addition, we will seek to improve industry understanding and knowledge of performance against this risk
Risk ref | Risk Title | Risk impact | Impact rationale | Target Risk impact | Target risk impact rationale | Risk factor / Control | PAP type | PAT Approach
5 | A fault with SVA Metering Equipment is not resolved, such that metered data is recorded incorrectly or cannot be retrieved | £35.8m |  | £34m |  | Improve understanding of Fault Resolution Root Causes | MOA | TAM
[7 empty] | MOA | PARMS
[7 empty] | All | MEM
Analysis
[6 empty] | Performance Management | All | Education
BSC Audit
TAPAP
[7 empty] | MOA | Peer Comparison
[7 empty] | MOA | EFR
For 2019/20, we propose to carry out analysis on the root causes of faults, and use the findings as well as output from detective techniques (the BSC Audit, TAM, PARMS and TAPAP) to identify material non-compliance in fault management processes. We also plan to set up routine Material Error Monitoring on fault resolution.
We propose to introduce additional incentives through Peer Comparison and support parties to improve their processes through education and EFR.
Risk ref | Risk Title | Risk impact | Impact rationale | Target Risk impact | Target risk impact rationale | Risk factor / Control | PAP type | PAT/Approach
23 | A fault with CVA Metering Equipment is not resolved, such that metered data is recorded incorrectly or cannot be retrieved | £30.2m |  | £28m |  | Lack of formal reporting | MOA | TAM
[7 empty] | MOA | PARMS
[7 empty] | MOA | Analysis
[6 empty] | Performance Management |  | Education
[7 empty] | MOA | BSC Audit
TAPAP
[7 empty] | MOA | MEM
[7 empty] | MOA | Peer Comparison
[7 empty] | MOA | EFR
[7 empty] | MOA | Re-qualification
[6 empty] | Future Changes | MOA | BSC Change
CVA Meter Operator Agents are the main Performance Assurance Party involved in this risk. For 2019/20, PAT deployment will be focused on enhancing measuring and monitoring of the risk and MOA performance. We will use additional data sources (including fault logs and the relevant PARMS Serial) and detective techniques to report on material non-compliance. If feasible we will set up routine Material Error Monitoring.
We will support CVA MOAs through education and incentive techniques to improve their processes, and deploy remedial PATs and escalation where necessary.
We will also maintain a watching brief on Issue 75, Use of Internet Protocol (IP) address based communication methods for CVA Metering Systems, which may have implications for this risk.
Risk ref | Risk Title | Risk impact | Impact rationale | Target Risk impact | Target risk impact rationale | Risk factor / Control | PAP type | PAT/Approach
18 | Revenue Protection processes are not managed sufficiently, such that unrecorded energy volumes are excluded from Settlement | £4.3m |  | £4m |  | Lack of data to understand Risk | All | Education
[7 empty] | Suppliers | TAPAP
[6 empty] | Ensure that identified volumes are submitted into Settlement | DC | BSC Audit
peer comparison
[7 empty] | DC | removal of qualification
EFR
[7 empty] | All | Trading Disputes
[6 empty] | Cross Industry Awareness | All | RFI
[6 empty] | Performance Management | All | Analysis
For 2019/20 the majority of the PAT deployment we are proposing is directed to finding out more about the risk and the data available to measure and monitor compliance with the BSC requirements.
We aim to carry out a piece of analysis, looking at use of alternative data sources (e.g. Theft Risk Assessment Service (TRAS) data, if feasible) to identify the amount of energy we should expect to see being adjusted in Settlement as confirmed revenue protection volumes. Detective PATs will be deployed to identify areas of material non-compliance at Suppliers and Data Collectors that will lead to this risk manifesting. We will support parties through education and incentive techniques to improve their processes, and deploy remedial PATs and escalation where necessary.

## PAT Deployment Detail
Risk Owner | Risk ref | Risk Title | Risk impact | Impact rationale | Target risk impact | Target risk impact rationale | Number of reviews per year | PAP type | PAT | Proposed PAT deployment and target outcome
Karen Lavelle/Sarah Ross | 001 | SVA Metering Point is registered incorrectly or not at all, such that metered data is not collected or aggregated | 5900000 | Impact is driven by backdated registrations in SMRS and assesment of the material impact through D0036 flow analysis. | £5.5m | Dissemination of education should lead to improvements in processing and a reduction of Risk impact although only a slight improvement expected. | 4 | Supplier LDSO MOA | Education | To reinforce the lessons relating to the importance and potential impacts on Settlements if SMRS is correct
[8 empty] | All | TAPAP/TAM | Monitor to see which parties are making the most changes and try to understand the root causes and if required conduct targeted site visits
[9 empty] | BSC Change | Review the validation process as set out in BSCP501 and ensure that it is still fit for purpose.
Karen Lavelle/Sarah Ross | 002 | SVA Metering System attributes held in the Supplier Meter Registration Service (SMRS) or by any party in the Supplier Hub are incorrect | 738938 | Impact driven by assessment of corrections to SMRS data | £650k | Dissemination of education should lead to improvements in processing and a reduction of Risk impact although only a slight improvement expected. | 1 | All | BSC Audit | Conduct a review of the work papers to ensure coverage of risk factors
[8 empty] | Supplier | Education | To explain the interactions between D0095 exceptions and Validated combinations (MDD) specifically highlighting Settlement impacting errors.
[9 empty] | TAPAP | To ascertain which parties are causing the most exceptions and try to understand root causes and conduct targeted site visits
[8 empty] | All | EFR | Applicable for Parties which receive a High/Medium Audit Issue around this risk
Jason Jackson | 004 | Changes to SVA Metering Equipment are not notified, such that all members of the Supplier Hub do not use the current Meter Technical Details | £7.7m | Impact is driven by assesment of updates made to Metering Equipment from DTN Data Flows, SMRS snapshots, and NM11 & HM11 PARMS Reports. | £6.7m | Dissemination of education should lead to improvements in processing and a reduction of Risk impact although only a slight improvement expected. Whilst Further improvements will result from improvements to the BSC Audit | 4 | All | Education | Conduct a review of Guideance Documents for their Content and Relevance
[9 empty] | Education | Conduct Workshop to improve on processes, their significance, and 'common problems'
[9 empty] | MEM | Introduce monitoring of D0215 performance
[8 empty] | LDSO MOA | MEM | Introduce monitoring of fault data obtained from DCUSA
[8 empty] | All | TAPAP | Conduct an Audit of D0215 processes
[9 empty] | BSC Audit | Conduct a review of the work papers to ensure coverage of risk factors
[9 empty] | RFI | review parties on the performance of their party agents in relation to Notification of Change processes
Chris Day | 006 | On a change of agent, Meter Technical Details are not transferred or processed correctly or at all, such that parties do not use the latest Meter Technical Details | £8m | Impact is driven by assesment of all Change of Agent Events which result in the transfer of MTDs from SMRS Snapshots. | £6m | Identification and rectification of errors identified through the TAM, PARMS, and BSC Audit is expected to improve the Risk Impact moderately | 4 | Supplier MOA | TAM | Maintain Current Audit of HH MTDs which reveiws the accuracy of MTDs and the physical Metering System
[8 empty] | All | BSC Audit | Conduct a review of the work papers to ensure coverage of risk factors
[9 empty] | PARMS | Maintain Current assessment of MTD quality and timeliness
[9 empty] | Peer Comp | Given the extensive historical investigations here, Peer comparison is a suitable for highlighting persistent long running poor performers.
[9 empty] | Qualification | Expand and reinforce system auditing within Qualification process to ensure uniformity and controls within Party systems.
George Player | 008 | SVA metered data is not processed or transferred correctly, or at all | £7.4m | Impact driven by assessment of the material error recorded from the Large EAC/AA MEM Report, SVAA data, and Trading disputes | £6m | Dissemination of education should lead to improvements alongside, Identification and rectification of errors identified through the PARMS, and BSC Audit is expected to improve the Risk Impact moderately | 4 | All | MEM | Introduce monitoring of NHH error volumes potentially used for assessing amount of post RF changes
[8 empty] | Supplier | BSC Audit | Conduct a review of the work papers to ensure coverage of risk factors
[9 empty] | Education | Conduct Erroneously large EAC AA education and education following Issue Group conclusions
[8 empty] | All | EFR | Applicable for Parties which receive a High/Medium Audit Issue around this risk
[9 empty] | TAPAP | To investigate HH data change root causes and small samples of SVA Complex and Shared Metering arrangements
[9 empty] | Analysis | Conduct Root Cause analysis for HH post RF Data changes
[9 empty] | Analysis | Conduct analysis on HH validation accuracy
Joanna Pasnik | 009 | The Data Aggregator does not process metered data correctly or at all, including transfer to SVAA, | £3m | Impact driven by two events identified as the main contributors to this risk, ELEXON assessed historical performance from the SVAA and Trading Disputes. | £2.5m | Improvements to pre-release testing and BSC Audit work papers should see a slight improvement in risk impact | 1 | DA | BSC Audit | Conduct a review of the work papers to ensure coverage of risk factors
[9 empty] | EFR | Applicable for Parties which receive a High/Medium Audit Issue around this risk
[9 empty] | Education | Impliment SMRS refresh process change
[9 empty] | Service delivery | Conduct a review of ELEXON pre-release testing, ensure roboust enough to prevent poor quality releases
[9 empty] | Near Miss Register | Record any missed DA files.
George Player | 010 | On change of Data Collector, meter read history is incorrect or not transferred such that sufficient history is not available for validating and estimating energy volumes | £2.7m | Impact is driven by assessment all Change of NHH Data Collector through historical change of Supplier events reported publically by Ofgem and change of DC events observed through quarterly snapshots of SMRS. | £2m | Improvements will be driven by EFR plans from the MTD CoS/CoA TAPAP due to related processes. | 1 | All | BSC Audit | Conduct a review of the work papers to ensure coverage of risk factors
[9 empty] | EFR | Applicable for Parties which receive a High/Medium Audit Issue around this risk and identification of consistent failings at individual DCs and suppliers for D170 processes
[9 empty] | PARMS | Serial NC11 – Maintain useage; but could be removed after the PAT review
Chris Day | 012 | SVA Metering System technical details are created incorrectly | £6.2m | Impact is driven by assesment of volumes associated with UMS related Consumption Component Class (CCC) IDs from the DTN Data Flows. | £5m | Moderate improvements will de driven by the identification and rectification of errors from BSC Audit, TAM, PARMs and completion of EFR Plans | 2 | Supplier LDSO MOA | BSC Audit | Conduct a review of the work papers to ensure coverage of risk factors
[9 empty] | TAM | Maintain the audit of MTD quality
[9 empty] | Education | Education piece could be supplied as part of Qualification information pack. This should include best practice advice around internal controls required to mitigate the risk.
[9 empty] | TAPAP | Review the results of recent TAPAP manage parties identified as non-compliant
[9 empty] | EFR | Applicable for Parties which receive a High/Medium Audit Issue around this risk, and those identified in the recent TAPAP
[9 empty] | Re-qualification | Applicalble when EFR plan milestones are consistently not met
[9 empty] | Removal of qualification | could be considered for materially significant issues.
[9 empty] | PARMS | HM13 Serial - Maintain useage; under reveiw through the PAF PAT Workstream
George Player | 013 | Manual adjustments to metered data are not completed correctly, or at all | £14.2m | Impact is driven by assement of incorrect Meter Technical Detail (MTDs) following the installation of a Meter from DTN Data Flows, SMRS snapshots, and HM11 & NM11 PARMs reporting | £13.5m | Slight improvements to the Risk impact will be driven by dissemination of Education leading to process improvements, alongside a review of the BSC Audit. | 1 | All | Education | Conduct education workshops and webinars on correct use and calculation of Manual Adjustments
[8 empty] | Supplier | MEM | Large EAC/AA - Maintain useage
[9 empty] | RFI | Request Parties logs of Manual Adjustments, assess root causes of any errors to support Educational aims
[8 empty] | All | TAPAP | Conduct an audit of Parties identified as non-compliant – conduct DTN testing to identify parties performing poorly
[8 empty] | All | BSC Audit | Conduct a review of the work papers to ensure coverage of risk factors
[8 empty] | Supplier | peer comparison | Ranking the poorest performing – would require an automated report to rank parties.
[9 empty] | Removal of Qualification | If parties are identified as acting fraudulently, then removal could be appropriate.
[8 empty] | All | EFR | Applicable for Parties which receive a High/Medium Audit Issue around this risk
Kat Higby | 014 | Agents are not appointed or de-appointed correctly, such that SMRS is not complete or up to date, members of the Supplier Hub do not hold the correct MPID of other Hub members or the appropriate agents are not appointed | £3m | Impact is driven by assessment of Change of MOA and DC for both HH and NHH from the SMRS snapshots. | £3m | Dissemination of education should lead to process improvements although the effect is expected to be muted. | 4 | Supplier | Education | Conduct education workshops and webinars clarifying the appointment process and it's settlement impacts
[9 empty] | Peer comparison | Ranking the poorest performing – would require an automated report to rank parties.
Karen Lavelle/Sarah Ross | 015 | SVA reference data is not created or transferred correctly, or at all, resulting in erroneous data in Settlement. | £0.59m | Impact is driven by assessment of all SVA MSIDs through the audit issues from the annual LLF Audit and MDD issues. | £0.5m | Slight improvements in impact are expected from the continuation of MDD validation and LLF Audit activites. | 1 | LDSO | BAU Control | LLF Audit - Maintain useage
[8 empty] | All | BAU Control | MDD Validation processing - Maintain useage
[9 empty] | BSC Audit | Conduct a review of the work papers to ensure coverage of risk factors
[9 empty] | Education | Conduct education workshops and webinars clarifying the reference data process and it's settlement impacts
Ryan Dale | 017 | Exception reports are not sufficiently managed, such that material exceptions are not addressed at all or in a timely manner | £0.2m | Impact is driven by assessment of all events that result in the transfer or amendment of MTDs and submission of or amendment to Consumption data from BSC Audit findings. | £0.15m | Moderate improvements to be driven by the improvements of the BSC Audit, and education dissemination | 4 | Supplier | Education | Conduct education workshops and webinars clarifying the HH and NHH exceptions process and their settlement impacts
[8 empty] | Supplier DC | BSC Audit | Conduct a review of the work papers to ensure coverage of risk factors - assist the Auditor in indenitifying the Material exceptions in order to provide clairty on materially impacting issues.
[9 empty] | peer comparison | Ranking the poorest performing – would require an automated report to rank parties.
[8 empty] | All | EFR | Applicable for Parties which receive a High/Medium Audit Issue around this risk
[8 empty] | Supplier | MEM | Introduce an Exception report which presents the live levels of Material Exceptions outstanding for each Party
Katie Wilkinson | 019 | A Volume Allocation Unit is registered incorrectly or not at all, such that the CDCA does not collect any or the relevant data | £0.48m | Impact is driven by assessment of the registration of new VAUs, the de-registration of VAUs and the transfer of BM Units from SVA to CVA and vice versa from the Registration database. | £0.48m | Maintain risk impact - low impact may not justify the expenditure on TAM changes, until risk is in focus. | 1 | Supplier LDSO CVA MOA | TAM | A specific sample undertaken to investigate MSIDs relating to Volume Allocation Units associated with Parties, which caused the Volume Allocation Unit registration errors, indentified from the Trading Disputes we have seen over the past 3 years.
Mike Smith | 020 | CVA Metering Equipment is installed, programmed or maintained incorrectly including where Commissioning is performed incorrectly or not at all | £14m | Impact is driven by assessment of all Metering Equipment in the CVA market from the CDCA database, alongside Trading Disputes and TAA findings. | £11.5m | Resumption of CM01 and CM02 PARMS, improvment of TAM and BSC Audit, and resulting EFR Plans should see a moderate to significant improvement in the impact of the risk | 2 | LDSO CVA MOA | Education | A review of educational material could be undertaken to ensure it is up-to-date and fit for purpose.
[9 empty] | TAM | Maintain annual audit of 5% of the CVA market - move to cyclical auditing to ensure coverage of market. scope to audit specific market segments i.e CoP specific
[9 empty] | PARMS | Resume useage of CM01 and CM02, which are reported by the CDCA and are related to proving tests and fault resolution processes
[8 empty] | All | MEM | Introduce a MEM report to regularly monitor error associated with this risk
[8 empty] | All | BSC Audit | Conduct a review of the work papers to ensure coverage of risk factors - widen scope to CVA auditing
[8 empty] | LDSO CVA MOA | TAPAP | Conduct an investigation of CVA metering activities
[9 empty] | Peer Comparison | introduce comparison based on CM01 and CM02 PARMs Serials
[8 empty] | All | EFR | Applicable for Parties which receive a High/Medium Audit Issue around this risk
Mike Smith | 022 | Changes to CVA Metering Equipment are not notified to CDCA | £5.2m | Impact is driven by assessment of changes made to CVA Metering equipment from the fault log of the CDCA. | £5m | dissemination of impoved educational materials will drive a slight improvement to the risk impact | 2 | All | Education | A review of educational material could be undertaken to ensure it is up-to-date and fit for purpose. Further industry days could be run with LDSOs to understand and explain impact. Days would be a split of educational sessions and workshops to discuss and overcome common issues and root causes.
[8 empty] | LDSO CVA MOA | MEM | Introduce monitoring obtained through Fault Data from DCUSA
[9 empty] | TAPAP | Conduct an audit of field activities, quality, assurance, and training
Mike Smith | 024 | CVA Metering System technical details are created incorrectly | £1.1m | Impact is driven by assessment of event which result in the production of MTDs from CDCA logs. | £1m | Improvements to and structured dissemination of educational materials should lead to a slight improvement in performance | 2 | Supplier LDSO CVA MOA | Education | Education piece could be supplied as part of Qualification information pack. This should include best practice advice around internal controls required to mitigate the risk.
[8 empty] | All | BSC Audit | MTD Quality is included in future audits for the SVA market only, review to investigate if widening scope to CVA would be appropriate.
[9 empty] | TAPAP | Investigate parties performing the process poorly
[9 empty] | TAM | Conduct a review of audit processes to ensure coverage of risk factors
[9 empty] | MEM | Introduce a MOP MTD data validation check against BSC Central Systems data
[9 empty] | Peer Comparison | Peer Comparison could be introduced to incentivise performance if we identify a decrease in MTD quality
[9 empty] | EFR | Applicable for Parties which receive a High/Medium Audit Issue around this risk.
[9 empty] | Re-qualification / Breach and Default | We could utilise this technique where rectification plan milestones are not met.
[9 empty] | Removal of Qualification | Considered for materially significant issues.
Katie Wilkinson | 025 | CVA reference data is not created or transferred correctly, or at all | £0.42m | Impact is driven by assessment of CVA MSIDs with LLFs applied and the number of BM Units with TLFs applied from LLF audits, BSC Audit Issues, and Trading Disputes. | £0.4m | improvements to workpapers and continuation of the LLF audit should drive a slight improvement to the risk impact | 1 | All | BSC Audit | Conduct a review of the work papers to ensure coverage of risk factors
[8 empty] | LDSO | BAU Control | LLF Audit - Maintain useage
Katie Wilkinson | 026 | Aggregation Rules in CDCA are incorrect such that CVA Metered Data is not correctly aggregated and the energy volumes required for Settlement are incorrect or missing | £0.1m | Impact is driven by Aggregation Rules currently registered in the CDCA. | £0.1m | continuation of current mitigation efforts, with a veiw to slightly improve the BSC Audit | 1 | All | Trading Disputes | Parties (or ELEXON) raise a Dispute when they become aware of an issue or error in order to rectify.
[9 empty] | TAM | Conduct a review of audit processes to ensure coverage of risk factors
[9 empty] | BSC Audit | Conduct a review of the work papers to ensure coverage of risk factors
[9 empty] | Education | A review of educational material could be undertaken to ensure it is up-to-date and fit for purpose.
Nick Baker/Roger Harris | 027 | Trading Parties do not or are unable to pay Trading Charges fully or at all, such that it triggers an Event of Default | £0.44m | Impact is driven by assessment of the Trading parties operating in the market from CDCA central systems. | £0.5m | Improvements to and structured dissemination of educational materials should lead to a slight improvement in performance, although external Market conditions could lead to an increase in the impact fo this risk over the PAOP | 1 | All | Education | Use Education during the initial Market Entry processes to inform Parties of the Credit requirements. Also repeat whenever needed. We could try to get more info from Parties on Business models and plans and work out what areas they need to know more about.
[9 empty] | Breach and Default | Could make a minimum level of credit compulsory, this would provide a better level of assurance to the whole industry
Nick Baker/Roger Harris | 028 | NETSO does not submit or submits incorrect Settlement data | £1.1m | Impact is based on assessment of the BSC Parties in the Balancing Mechanism from the NETSO Bids & Offers and Net Imbalance Volumes sourced from SAA Systems. | £1.0m | Slight improvements to the Service level agreements should lead to a slight improvement in performance | 1 | All | Service Levels | Conduct a review of Contractual Service Level Agreements to ensure they are fit-for-purpose
[9 empty] | Service Levels | Conduct analysis of the performance of NETSO, are Service Level Agreements being met.
Nick Baker/Roger Harris | 029 | The SAA's calculations and processing are incorrect or use incorrect data | £0.5m | Impact is driven by assessment of all BSC Parties, however scale of error will vary between parties, information has been gathered from BSC Central Systems. | £0.5m | Limited PAT availability for Risk, although improvements will be investigated throughout the year. Maintain risk impact | 1 | All | BSC Audit | Conduct a review of the work papers to ensure coverage of risk factors
Nick Baker/Roger Harris | 030 | The ECVAA does not carry out processes correctly, such that output files are inaccurate | £2.1m | Impact is driven by assessment of parties operating the contract notification and all Parties which receive notifications. | £2.1m | Limited PAT availability for Risk, although improvements will be investigated throughout the year. Maintain risk impact | 1 | All | BSC Audit | Conduct a review of the work papers to ensure coverage of risk factors
Nick Baker/Roger Harris | 031 | The FAA does not accurately process Trading Charges or calculate ad-hoc charges correctly, such that Advice Notes are incorrect | £0.05m | Impact is driven by assessment of Trading Charges and Default Funding Shares from Central Systems. | £0.05m | Limited PAT availability for Risk, although improvements will be investigated throughout the year. Maintain risk impact | 1 | All | BSC Audit | Conduct a review of the work papers to ensure coverage of risk factors
Nick Baker/Roger Harris | 032 | Manual adjustments to CVA Metered Data are not completed correctly, or at all | £1.5m | Maintain the risk Improve data oversight over the Risk Monitoring/reporting tool to provide further detail | £1.5m | Limited PAT availability for Risk, although improvements will be investigated throughout the year. Maintain risk impact | 2 | All | BSC Audit | Conduct a review of the work papers to ensure coverage of risk factors
[8 empty] | All | TAPAP | Conduct investigation into CVA Manual adjustments for their compliance and accuracy
Nick Baker/Roger Harris | 033 | An Interconnector Administrator does not submit, or submits inaccurate BM Unit Metered Volume data | £0.29m | Impact is driven by assessment of BM Metered data submitted by the Interconnector Administrator from the Central Systems. | £0.29m | Limited PAT availability for Risk, although improvements will be investigated throughout the year. Maintain risk impact | 1 | All | BSC Audit | Conduct a review of the work papers to ensure coverage of risk factors
Nick Baker/Roger Harris | 034 | The SVAA does not process or transfer the correct data or does not use approved default data. | £0.18m | Impact is driven by assessment of SVA Data processing from the Volume Allocation Run received from Data Aggregator. | £0.18m | Limited PAT availability for Risk, although improvements will be investigated throughout the year. Maintain risk impact | 2 | All | BSC Audit | Conduct a review of the work papers to ensure coverage of risk factors

## Events Log
Area | Event | Consequence / risk management impact | Notes | Risk mitigation - PATs and other
Agents | Lack of (strong) commercial contract between Supplier and SMRS-registered Agent, e.g. where the customer has directly appointed agents - Customer Preferred Agents | Could prove harder to resolve issues. Suppliers report it may be harder to influence Settlement performance. Some HHCs may not undertake manual reads where the meter is unable to remotely dial. Some HHMOAs do not install alternative comms on sites where the cost of doing so is prohibitive. Some HHDCs are not completing HHDC Annual Site visits. | PAF can only respond to non-compliances and give guidance on best practice. Supplier Hub model being considered under Ofgem Significant Code Review. | - Education: PAB / ELEXON issue guidance on BSC compliance and best practice - Peer Comparison: existing Agent PC and new proposed reports for 2019/20
Non-standardised processes | Variation between parties with system requirements, data and flow formats, and work arounds / manual entering of data. | Will make some risks more prevalent with certain PAP combinations, and could create additional work for managing different formats etc. Not necessarily a non-compliance. | Party Service Line 100 - describes good practice. PAF can only respond to non-compliances and give guidance on best practice. | None identified for 2019/20
Volume and type of industry change | Parties feel the rate and source of change is unprecedented - BSC and wider. Different solutions used for similar fixes or improvements - duplicating effort. There is concern that Party Agent requirements are poorly considered, late in their specification and lacking the required detail. | Parties could have conflicting demands on resource. Harder to design implementation of change in systems / processes. Complex and difficult commercial funding agreements between parties. Harder to invest in changes if there's uncertainty about benefits and further future change. Will make some risks more prevalent, where they are impacted by change directly, or resources are taken away from BAU or working exceptions and issues. Cumulative impacts may not be obvious during the change development process. | Includes smart meter rollout | - Impact Assessments for Mods, CPs and releases identify where workloads may be concentrating. - PAB Strategy considers this in directing focus of PAF to focus on priority risks - Risk Manager conversations with PAPs identifies any particular concerns
Change management of system and process change | Management of change to systems and processes driven from BSC Modifications or Change Proposals, or changes by individual parties. | Parties making changes that introduce delays or non-compliances, or not making required changes to be or remain compliant. This could cover significant increase in portfolio size that means existing systems and processes can't support the BSC obligations. | Many risks potentially affected. The PAF can facilitate guidance on best practice and deploy mitigating techniques to support change management. PSL100 - contains some relevant points on good practice. | - Re-Qualification: ELEXON issue guidance on material changes
Knowledge within BSC Parties and Party Agents | Loss of knowledge about the BSC arrangements within existing participants, and a high level of new entrants without experience, in particular for large SVA and CVA site metering. | Increasing level of non-compliances and systems or processes that don't follow best practice leading to more errors, more inconsistent and incomplete data exchanges, more manual work, more exceptions and less robust issue and exception management. | Party Service Line 100 - describes good practice including adequate training of staff. PAF can only respond to non-compliances and give guidance on best practice. | - Education: PAB / ELEXON issue guidance on BSC compliance and best practice for key risks and in higher risk scenarios, e.g. new parties - (Re)Qualification: SAD includes questions on staff training and use of working procedures, including for disaster recovery
Capability to manage Half Hourly Settlement processes | Due to growth in population of Half Hourly settled sites and new smaller Suppliers taking on HH meters without the detailed knowledge of the underlying processes and management techniques. | Reduced performance of Half Hourly Settlement and increase in non-compliant processes, issues and errors. | A number of SVA risks potentially affected. The PAF can facilitate guidance on best practice and specifically deploy Education as a mitigating technique. | - Education: Issue guidance on best practice and BSC Obligations - EFR: ELEXON will work with Parties to improve performance to target levels
Third parties more involved in BSC processes, and non-traditional business models | Increase in number of third party agents or outsourced providers used by customers or BSC Parties / Party Agents to perform actions that directly or indirectly touch on BSC and Settlement data and activities | Actions may not be completed to time or quality or at all, information may not be provided at all or completely / correctly and issues can be harder to resolve. | There is no provision within the BSC to give third parties responsibilities for compliance around Settlement actions / data - this rests with BSC Parties and Qualified Persons. | - ELEXON and the PAB may engage with Ofgem on industry developments that might exacerbate this - Peer Comparison: (and other reporting) may indicate to PAPs where third parties are a cause of material non-compliance
Meter Exchanges | Due to technology changes (smart meter rollout) and interoperability issues of metering equipment, the rate of meter exchanges is high. | More events means more opportunity for failure in the meter exchange process, and resources diverted from other activities such as fault and exception resolution. Also, meter exchanges may uncover historic issues which should be rectified. |  | - Education: review guidance notes and workshop common issues with risk 4 - changes to SVA metering equipment
Priority of Settlement Risk | Performance Assurance Parties do not prioritise risks to Settlement due to lack of awareness and/or resource constraints including from external events such as Government policy decisions. | Less resource available for maintaining compliance with BSC processes and fixing non-compliances and issues in a timely and best practice way. | An example will be the efforts being put into the Smart Meter rollout or price caps. Party engagement with OSM and Risk Manager give opportunities for discussing any related issues or points of concern. | - Compelling communication aimed at senior managers, highlighting implications of non-compliance, benefits of mitigation within BSC and wider, and how we'll be asking them to help mitigate risks in the year. - Peer Comparison: existing, and new proposed reports for 2019/20
Capability to manage Half Hourly (HH) settlement processes | Growth in population of Half Hourly settled sites after P272 and new smaller Suppliers taking on HH Meters potentially without the detailed knowledge of the underlying processes and management techniques, which can be different from Non-Half Hourly. | Reduced performance of Half Hourly Settlement and increase in non-compliant processes, issues and errors, multiple risks. | OSMs will support parties with individual areas of material non-compliance or education requirements | - Education: Proposed to draft guidance on achieving HH Settlement standards - Material Error Monitoring: investigate establishing MEM on fault resolution - TAPAP: investigate HH Settlement data change root causes, including Complex and Shared Metering
Party failure | Supplier of Last Resort (SoLR) events, and other instances where Parties or Party Agents cease operating | Can result in historical issues being harder to fix if the previous Party or Party Agent is not available to aid resolution. May affect multiple risks. The "new" Supplier is not liable for Settlement data/days (or error) before taking on the MPID, therefore there are limits on the PATs we can deploy to manage Settlement-impacting error for the "old" Supplier's period of responsibliity. Error could remain uncorrected for more instances than previously anticipated, if the rate of SoLRs / number of MSIDs involved is higher than forecast. | Separate from the risk of Party Defaults. | - BSC Audit: proposed to review BSCCo and Supplier delivery of the SoLR processes to check for compliance and best practice
SVA Export, Generation, Complex and Shared Metering | Limited experience across the industry in set up and management of non-standard metering | Metering risks may be more prevalent and harder to resolve issues. | Modification P379 ‘Multiple Suppliers through Meter Splitting’ could be implemented early 2020 - within the 2019/20 assurance year, potentially introducing a new process / Party Agent type related to shared metering - facilitating multiple Suppliers per meter. | - The CoP4 Working Group, starting Winter 2018/19, may raise some relevant points for this Event e.g. around commissioning of sites with export. - Qualification: for new Party Agent types, dependent on P379 progress - Education: review guidance notes and workshop common issues with risk 4 - changes to SVA metering equipment
Change of Supplier | Increasing rates of churn as customers change Supplier more frequently | More "change of…" events leading to more opportunities for non-compliance with processes, which need to be addressed by several Supplier Hubs. Likely to affect multiple risks. |  | - Monitoring CoS numbers and the number of smart Meters that lose interoperability after CoS. - Detective PATs: monitoring compliance - Education: Good practice in managing change events e.g. through risk 7, retrieval of metered data.
System and internal process changes | BSC Modifications and Change Proposals may require PAPs to make amendments to their systems. Changes may introduce non-compliance if not delivered correctly. Conversely, not making required changes (in time) would make parties non-compliant. | Could affect any or multiple risks. | Party Service Line 100 - describes good practice including change control processes. This Event could cover significant increase in a PAP's portfolio size that means existing systems and processes can't support the BSC obligations. Party engagement with OSM, Risk Manager and BSC Auditor give opportunities for discussing implementation of changes and any related issues or points of concern. | - Impact Assessments by PAPs and the PAA of BSC Change should identify where implementation / failure to implement was particularly likely to lead to material non-compliance by parties. - Near-miss register to capture issues parties see early on from BSC Change implementation. - Re-Qualification: for changes that are deemed material in relevant PAP's Risk & Impact Assessments. The PAB can require Re-Qualification - TAPAP: PAB could direct a review of PAPs' RIA processes to check it reflects best practice.
Remote communications failures | Systemic failure of one of more communications systems or networks resulting in a large proportion of remote read meters being uncontactable for a period of time. | Reads can't be retrieved remotely, and other aspects of the meter set up may not be able to be changed remotely, requiring site visits that may take longer to carry out. | The BSC does not mandate that comms must be installed; it is assumed that the Supplier will meet BSC standards for actual energy volumes regardless of remote communications to site. For maintenance of comms, there are no obligations for SVA NHH faults to be fixed, but SVA HH comms equipment must be fixed. Note that there is a chance of comms networks (2G) being discontinued in future years. See BSC Issues 73 and 75. | - Manage the risk if a systemic failure happens, e.g. determine what level of risk is tolerable, and agree risk mitigation e.g. a process for getting all the data / reads in once the comms is re-established.
Brexit | The uncertainty for BSC Parties and their agents around Brexit and the actual events during and after Brexit, lead to for example reduced investment, higher costs, staffing issues, difficulty accessing parts and equipment. | Uncertainty could perhaps mean parties are less likely to invest in systems, processes and staff. Reduced Settlement performance and increase in non-compliant processes, issues and errors. Increase in Credit Defaults, inability to pay Trading Charges, and other non-BSC Obligations. | BEIS has published some information about a no-deal scenario. Not anticipated to be major impacts on the BSC arrangements. Party engagement with OSM and Risk Manager give opportunities for discussing any related issues or points of concern. | None identified for 2019/20
Industry Policies | Government led policies such as the default tariff price cap affect decisions made by BSC Parties and their agents directly or indirectly related to BSC obligations, and may change customer behaviour such as changing Supplier and acceptance of new types of meters and services. | Reduced Settlement performance and increase in non-compliant processes, issues and errors. Increase in Credit Defaults, inability to pay Trading Charges, and other non-BSC Obligations. | Many risks potentially affected. The PAF can facilitate guidance on best practice and deploy mitigating techniques to support change management. PSL100 - contains some relevant points on good practice. | - ELEXON issue impact assessments to industry bodies relating to policy - Manage industry policy changes with parties via their OSM
Capacity Market Payments | P378 ’Introduction of a CM Supplier Interim Charge’ - Change going through to collect payments during the interim period of the Capactiy Market having been suspended. | Potential impact on the financial position of Parties subject to payments, Leading to uncertain financial positions. | Await reposnce from OFGEM | - ELEXON are processing the change designed to mitigate negative impacts of CM Suspension
|  | Change should operate to collect the payments from Parties at an equivilent rate, to mitigate the impact of large payments required following removal of suspension. | Await consultation responces
Market-wide Half-Hourly Settlement | Transition to a new operating model | Risks of material non-compliance impacting Settlement during the transition and in the early days of new market operations | Current implementation date is 2023 | - Project approach proposed in PAB Strategy - PAB sub-group tracking progress

## ROP Change Log
Version | Effective From Date | Change description | Status
0.1 | 2019-01-31 | First draft | Proposed